## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. Since Product acceptance is from the perspective of the end-user, only add User Stories that pertain to the Owner or Buyer and do not include User Stories specifically for the REST API service (e.g. AS a developer...). As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. Note that there are separate columns for each sprint. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2231-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions and cross-team testing.
Team Name | term-swen-261-07-e LAWNN
Testing Team Name | fill in when doing cross-team testing

## Test Plan
User Story | Acceptance Criterion | Peer Review (Pass/Fail) | Tester initials; date; comments (required if test failed)
As a helper I want to see a list of needs so that I choose what to contribute to. | Given that I am on the u-fund site when I am not on the Needs page then I must see a means to navigate to the Needs page. | Pass
| Given that I am not on the Needs page when I choose the Needs page then I am taken to the Needs page. | Pass
| Given that I am on the Needs page when there are no needs in the cupboard I see an empty page | Pass
| Given that I am on the Needs page when there are needs in the cupboard then I see each need and short description. | Pass
| Given that I am on the Needs page when there are needs in the cupboard then I see a means to add each need to my funding basket. | Pass
As a helper I want to log in using a username so that I can access helper-only capabilities. | Given I enter a username when the username exists already then I expect to be logged in that user | Pass
| Given I enter a username when the username does not exist already then I expect a new user to be created, and I get logged in as them | Pass
As a manager I want to log in using a username so that I can access manager-only capabilities. | Given I enter "admin" when I enter my username then I expect to be logged in as a manager | Pass
As a manager I want to create a new need so that it is added to the cupboard and available to purchase. | Given the need does not exist yet, when I create a new need, I expect to see it appear in the cupboard | Pass
| Given the need already exists, when I try to create one with the same name or id, I expect to be notified of some kind of error | Pass
As a manager I want to edit needs so that needs are kept up to date | Given I am a manager editing a need, when I update the name of the need, then I expect the name of the need to change | Pass
| Given I am a manager editing a need, when I update the description of the need, then I expect the description of the need to change | Pass
| Given I am a manager editing a need, when I update the cost of the need, then I expect the cost of the need to change | Pass
As a manager I want to delete a need so that it is no longer in the cupboard | Given the need exists, when I delete a need, I expect to no longer see it appear in the needs cupboard | Pass
As a user (helper or manager) I want to search the cupboard for needs whose name contains the given text, so that I can find specific needs | Given a search bar, when I type in a need's title, I expect to see it appear in the results | Pass
| Given a search bar, when I type in a title that does not correspond to a need, I expect to see no results | Pass
As a user (helper or manager) I want to view the entire cupboard so that I can see all the needs in the cupboard | Given the im on the inventory page as a helper or manager, I expect to see the entire needs cupboard | Pass
As a user (helper or manager) I want to view a single need so that I can see it’s details. | Given I click on a need, I expect to see a detail page with more information about the need | Pass
AS a Helper I WANT to be able to sort the list of needs by various metrics SO THAT I am presented with a list of needs that is more relevant to what I am looking for. | Given I am on the inventory page when I select a metric from the sortby dropdown then the inventory list will refresh and be sorted by that metric | Pass | ALL TESTED BY M.D AND Z.S.
As a Manager I want to be able to mark needs as urgent so that Helpers see that need and might contribute to it over nonurgent needs | Given the ability to tag needs as urgent when I tag a needs as urgent then Helpers will prioritize donating to it over nonurgent needs.
As a Helper I want to be able to spend above a certain threshold on an up-and-coming villain’s needs so that I unlock the ability to name that villain.